## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W
1 | User Registration and Authentication |  | 12 | 12 | 0 |  |  |  |  | 100%
1.1 | User Interface Login | Cristian Santaroni | 2 | 2 | 0 | 1 | 2023-09-28 | 2023-09-28 | 1 | 100% | bar: WEEK 1 M
1.2 | Implement user registration with Facebook login | Francesco Fortunato | 2 | 2 | 0 | 1 | 2023-09-29 | 2023-09-29 | 1 | 100% | bar: WEEK 1 T
1.3 | Develop user authentication system | Cristian Santaroni & Francesco Fortunato | 8 | 8 | 0 | 1 | 2023-09-30 | 2023-09-30 | 1 | 100% | bar: WEEK 1 T to WEEK 2 F
2 | Point of Interest (POI) Information |  | 10 | 0 | 10 |  |  |  |  | 0%
2.1 | OpenTripMap API Integration | Francesco Fortunato | 2 | 0 | 2 | 2 | 2023-10-02 | 2023-10-02 | 1 | 0% | bar: WEEK 4 M
2.3 | OpenWeatherMap API Integration | Francesco Fortunato | 2 | 0 | 2 | 2 | 2023-10-02 | 2023-10-02 | 1 | 0%
2.2 | HERE API Integration | Cristian Santaroni | 2 | 0 | 2 | 2 | 2023-10-03 | 2023-10-03 | 1 | 0%
2.4 | User Interface Research Bar | Cristian Santaroni | 4 | 0 | 4 | 2 | 2023-10-05 | 2023-10-05 | 1 | 0%
2.5 | User Interface List POI | Francesco Fortunato | 3 | 0 | 3 | 2 | 2023-10-06 | 2023-10-06 | 1 | 0%
2.6 | User Interface Details POI | Cristian Santaroni | 3.5 | 0 | 3.5 | 2 | 2023-10-07 | 2023-10-07 | 1 | 0%
3 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0! | bar: WEEK 7 M
3.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.2.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
3.3.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
4.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.4 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 22 | 12 | 10 | 30 | 0.73333 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 22 | 21.2667 | 20.5333 | 19.8 | 19.0667 | 18.3333 | 17.6 | 16.8667 | 16.1333 | 15.4 | 14.6667 | 13.9333 | 13.2 | 12.4667 | 11.7333 | 11 | 10.2667 | 9.5333 | 8.8 | 8.0667 | 7.3333 | 6.6 | 5.8667 | 5.1333 | 4.4 | 3.6667 | 2.9333 | 2.2 | 1.4667 | 0.73333 | 0 | 0 | 0
[10 empty] | ESTIMATE | 22 | 20 | 17 | 15 | 13 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 367
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 2; WEEK 1 T: 3; WEEK 1 W: 2; WEEK 1 R: 2; WEEK 1 F: 3 | 12
[10 empty] | HRS REMAINING | 20 | 17 | 15 | 13 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 355
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
2 | 1 | User Registration and Authentication | User Interface Login | Realizing the html page which is composed by a welcome message with a button that allows to log-in with its own facebook account. | Francesco Fortunato | 2 | Completed |  | Not Started | 1
2 | 1 | User Registration and Authentication | Implement user registration with Facebook login | Implement FB authentication flow | Cristian Santaroni | 2 | Completed |  | In Progress | 2
1 | 1 | User Registration and Authentication | Develop user authentication system | Implement the flow which recognize if a user after log-in with its facebook account has or not an account in PlaceAdvisor. If the user doesn't have an account, it should be created automatically and saved in the db, otherwise he should be redirected in the home-page | Cristian Santaroni & Francesco Fortunato | 8 | In Progress |  | Completed | 4
[6 empty] | 8 | Not Started |  |  | 8
[6 empty] | 4 | Not Started |  |  | 16
[6 empty] | 80 |  |  |  | 24
[6 empty] | 16 |  |  |  | 40
[6 empty] | 8 |  |  |  | 80
4
2
24
40
8

## User Stories or Tasks
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES or TASKS
TASK TITLE | TASK DESCRIPTION | ADDED BY | DATED ADDED
User Interface Login | Realizing the html page which is composed by a welcome message with a button that allows to log-in with its own facebook account. | Francesco Fortunato | 2023-09-28
Implement user registration with Facebook login | Implement FB authentication flow | Cristian Santaroni | 2023-09-28
Develop user authentication system |  | Cristian Santaroni & Francesco Fortunato | 2023-09-28