## EXAMPLE Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART | [60 empty] | https://goo.gl/ejIdKR
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Leon W | 40 | 40 | 0 |  | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2017-03-15 | 2017-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2017-03-15 | 2017-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2017-03-16 | 2017-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2017-03-17 | 2017-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2017-03-18 | 2017-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2017-03-23 | 2017-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope and Goal Setting | Steve L | 80 | 70 | 10 |  | 2017-03-24 | 2017-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2017-03-29 | 2017-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status and Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Leon W | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance/Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET

## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | User Registration and Authentication |  | 14 | 14 | 0 |  |  |  |  | 100%
1.1 | User Interface Login | Cristian Santaroni | 2 | 2 | 0 | 1 | 2023-09-26 | 2023-09-27 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | Implement user registration with Facebook login | Francesco Fortunato | 4 | 4 | 0 | 1 | 2023-09-27 | 2023-09-30 | 4 | 100% | bar: WEEK 1 T to WEEK 2 F
1.3 | Develop user authentication system | Cristian Santaroni & Francesco Fortunato | 8 | 8 | 0 | 1 | 2023-09-27 | 2023-09-30 | 4 | 100% | bar: WEEK 1 M to WEEK 2 F
2 | Point of Interest (POI) Information |  | 16 | 3 | 13 |  |  |  |  | 18.75%
2.1 | OpenTripMap API Integration | Christian Santaroni | 4 | 2 | 2 | 2 | 2023-10-02 | 2023-10-06 | 5 | 50% | bar: WEEK 4 M
2.3 | OpenWeatherMap API Integration | Christian Santaroni | 4 | 0 | 4 | 2 | 2023-10-04 | 2023-10-06 | 3 | 0%
2.2 | HERE API Integration | Francesco Fortunato | 4 | 0 | 4 | 2 | 2023-10-03 | 2023-10-06 | 4 | 0%
2.4 | User Interface Research Bar | Cristian Santaroni | 4 | 1 | 3 | 2 | 2023-10-02 | 2023-10-06 | 5 | 25%
2.5 | User Interface List POI | Francesco Fortunato | 4 | 1 | 3 | 2 | 2023-10-02 | 2023-10-06 | 5 | 25%
2.6 | User Interface Details POI | Cristian Santaroni | 4.5 | 2 | 2.5 | 2 | 2023-10-02 | 2023-10-07 | 6 | 44.44%
3 | User Reviews and Ratings |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
3.1 | Develop API endpoints to retrieve reviews and ratings for specific POIs | Francesco Fortunato |  | 0 | 0 | 2 |  |  | 1 | #DIV/0! | bar: WEEK 7 M
3.2 | Create a database for storing user reviews and ratings | Cristian Santaroni |  | 0 | 0 | 2 |  |  | 1 | #DIV/0!
3.3 | User Interface for display and submit reviews |  |  | 0 | 0 | 2 |  |  | 1 | #DIV/0!
4 |  |  | 0 | 0 | 0 |  |  |  |  | #DIV/0!
4.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.2 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
4.3 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
5
5.1
6
6.1 |  |  |  |  | 0 |  |  |  | 1 | #DIV/0!
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 30 | 17 | 13 | 34 | 0.88235 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 30 | 29.1176 | 28.2353 | 27.3529 | 26.4706 | 25.5882 | 24.7059 | 23.8235 | 22.9412 | 22.0588 | 21.1765 | 20.2941 | 19.4118 | 18.5294 | 17.6471 | 16.7647 | 15.8824 | 15 | 14.1176 | 13.2353 | 12.3529 | 11.4706 | 10.5882 | 9.7059 | 8.8235 | 7.9412 | 7.0588 | 6.1765 | 5.2941 | 4.4118 | 3.5294 | 0 | 0 | 0 | 0
[10 empty] | ESTIMATE | 30 | 28 | 25 | 23 | 21 | 18 | 13 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 392
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 2; WEEK 1 T: 3; WEEK 1 W: 2; WEEK 1 R: 2; WEEK 1 F: 3; WEEK 2 M: 5; WEEK 2 T: 4 | 21
[10 empty] | HRS REMAINING | 28 | 25 | 23 | 21 | 18 | 13 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 371
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET | bar: WEEK 7 R to WEEK 7 F

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
2 | 1 | User Registration and Authentication | User Interface Login | Realizing the html page which is composed by a welcome message with a button that allows to log-in with its own facebook account. | Francesco Fortunato | 2 | Completed |  | Not Started | 1
2 | 1 | User Registration and Authentication | Implement user registration with Facebook login | Implement FB authentication flow | Cristian Santaroni | 2 | Completed |  | In Progress | 2
1 | 1 | User Registration and Authentication | Develop user authentication system | Implement the flow which recognize if a user after log-in with its facebook account has or not an account in PlaceAdvisor. If the user doesn't have an account, it should be created automatically and saved in the db, otherwise he should be redirected in the home-page | Cristian Santaroni & Francesco Fortunato | 8 | In Progress |  | Completed | 4
1 | 2 | Point of Interest (POI) Information | OpenTrip Map API integration | Using the API the user should be able to check all the places within a ray for a specific city also specifying which type of place he wants to see |  | 8 | Completed |  |  | 8
2 | 2 | Point of Interest (POI) Information | OpenWeatherMap API Integration | The user should be able to check the weather by displaying an icon indicating the various types of weather. This is done by calling the OpenWeatherMap API which return all this information |  | 4 | Not Started |  |  | 16
2 | 2 | Point of Interest (POI) Information | HERE API integration | The user should be able to identify the place inside the map, this is done by calling HERE API which marks the point of interest. |  | 80 | In Progress |  |  | 24
1 | 2 | Point of Interest (POI) Information | User Interface Research Bar | The user should be able to searche places starting from a city, deciding which is the ray and specifiyng which is the category of the place he is interested. This is done by inserting a search bar for the cities, a drop-down menu for the category of the places and an area in which the user can insert the ray. |  | 16 | In Progress |  |  | 40
1 | 2 | Point of Interest (POI) Information | User Interface Details POI | Whenever is possible it is useful to show to the user, all the details of the place, like an historical description if it is an archeological place etc. |  | 8 | In Progress |  |  | 80
4
2
24
40
8

## User Stories
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES
As a | I want to | In order to | ADDED BY | DATED ADDED
New user | register and log in inside the web application using my Facebook account | access the service | Francesco Fortunato | 2023-09-28
Registered User | be able to log in with my Facebook credentials | save time and avoid creating a new account | Cristian Santaroni | 2023-09-28
User | search for points of interest in a specific area or city | discover new places to visit | Cristian Santaroni & Francesco Fortunato | 2023-09-28
User | view detailed information about a point of interest, including its address, historical facts, and other relevant details | make informed decisions about visiting it
User | read reviews and ratings of points of interest from other users | get insights into their experiences
User | leave my own reviews and ratings for points of interest | share my opinions and help others make informed choices
User | upload and attach photos to points of interest | visually share my experiences with others
User | release some feedback for the website | improve the quality of service
User | initiate a real-time chat with customer support representatives | get assistance with app-related issues
User | access to analytics and insights about points of interest | gain a better understanding of popular destinations and trends
Customer Care | log in inside web application | find if there are some users that need help
Customer Care | chat with users of the web application | assist the users and respond to their questions