## BLANK Gantt Chart & Burndown
SCRUM PROJECT MANAGEMENT GANTT CHART
GANTT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | User Registration and Authentication |  | 14 | 14 | 0 |  |  |  |  | 100%
1.1 | User Interface Login | Cristian Santaroni | 2 | 2 | 0 | 1 | 2023-09-26 | 2023-09-27 | 2 | 100% | bar: WEEK 1 M
1.2 | Implement user registration with Facebook login | Francesco Fortunato | 4 | 4 | 0 | 1 | 2023-09-27 | 2023-09-30 | 4 | 100% | bar: WEEK 1 T to WEEK 2 F
1.3 | Develop user authentication system | Cristian Santaroni & Francesco Fortunato | 8 | 8 | 0 | 1 | 2023-09-27 | 2023-09-30 | 4 | 100% | bar: WEEK 1 T to WEEK 2 F
2 | Point of Interest (POI) Information |  | 15 | 15 | 0 |  |  |  |  | 100%
2.1 | OpenTripMap API Integration | Cristian Santaroni | 2 | 2 | 0 | 2 | 2023-10-02 | 2023-10-06 | 5 | 100%
2.3 | OpenWeatherMap API Integration | Cristian Santaroni | 2 | 2 | 0 | 2 | 2023-10-04 | 2023-10-06 | 3 | 100%
2.2 | HERE API Integration | Francesco Fortunato | 2 | 2 | 0 | 2 | 2023-10-03 | 2023-10-06 | 4 | 100%
2.4 | User Interface Research Bar | Cristian Santaroni | 3 | 3 | 0 | 2 | 2023-10-02 | 2023-10-06 | 5 | 100%
2.5 | User Interface List POI | Francesco Fortunato | 3 | 3 | 0 | 2 | 2023-10-02 | 2023-10-06 | 5 | 100%
2.6 | User Interface Details POI | Cristian Santaroni | 3 | 3 | 0 | 2 | 2023-10-02 | 2023-10-07 | 6 | 100%
3 | User Reviews and Ratings |  | 12 | 12 | 0 |  |  |  |  | 100%
3.1 | Develop API endpoints to retrieve reviews and ratings for specific POIs | Francesco Fortunato | 8 | 8 | 0 | 2 | 2023-10-04 | 2023-10-07 | 4 | 100%
3.2 | Create a database for storing user reviews and ratings | Cristian Santaroni | 1 | 1 | 0 | 2 | 2023-10-04 | 2023-10-07 | 4 | 100%
3.3 | User Interface for display and submit reviews | Cristian Santaroni | 3 | 3 | 0 | 2 | 2023-10-04 | 2023-10-07 | 4 | 100%
4 | Photo Upload Integration |  | 15 | 15 | 0 |  |  |  |  | 100%
4.1 | Integrate Google Photos API | Cristian Santaroni | 3 | 3 | 0 | 3 | 2023-10-09 | 2023-10-11 | 3 | 100% | bar: WEEK 2 M to WEEK 3 T
4.2 | Implement choosing photo | Francesco Fortunato | 6 | 6 | 0 | 3 | 2023-10-09 | 2023-10-11 | 3 | 100% | bar: WEEK 2 M to WEEK 3 T
4.3 | Implement attaching photo to review | Cristian Santaroni | 6 | 6 | 0 | 3 | 2023-10-09 | 2023-10-11 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
5 | Feedback Service |  | 10 | 10 | 0 |  |  |  |  | 100%
5.1 | Create a feedback form for users | Cristian Santaroni | 4 | 4 | 0 | 3 | 2023-10-11 | 2023-10-13 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
5.2 | Develop a backend system for feedback | Cristian Santaroni & Francesco Fortunato | 6 | 6 | 0 | 3 | 2023-10-11 | 2023-10-13 | 3 | 100% | bar: WEEK 3 W to WEEK 3 F
6 | API Documentation |  | 8 | 8 | 0 |  |  |  |  | 100%
6.1 | Create and publish API documentation | Cristian Santaroni & Francesco Fortunato | 8 | 8 | 0 | 4 | 2023-10-16 | 2023-10-20 | 5 | 100% | bar: WEEK 4 M to WEEK 4 W
7 | User Registration and Authentication (Pt. 2) |  | 10 | 10 | 0 |  |  |  |  | 100%
7.1 | Implement authentication sessions (JWT) | Francesco Fortunato | 8 | 8 | 0 | 4 | 2023-10-16 | 2023-10-20 | 5 | 100% | bar: WEEK 4 W to WEEK 4 R
7.2 | Enable HTTPS for secure communication | Cristian Santaroni | 2 | 2 | 0 | 4 | 2023-10-16 | 2023-10-20 | 5 | 100% | bar: WEEK 4 W to WEEK 4 R
8 | Docker Compose Implementation |  | 6 | 6 | 0 |  |  |  |  | 100%
8.1 | Docker Compose Integration | Cristian Santaroni & Francesco Fortunato | 6 | 6 | 0 | 4 | 2023-10-16 | 2023-10-20 | 5 | 100% | bar: WEEK 4 R to WEEK 5 F
9 | Customer Care Chat |  | 8 | 8 | 0 |  |  |  |  | 100%
9.1 | Implement a real-time chat service | Cristian Santaroni & Francesco Fortunato | 8 | 8 | 0 | 5 | 2023-10-23 | 2023-10-25 | 3 | 100%
10 | Dashboard with Kibana and Elasticsearch (supported by Logstash) |  | 2 | 2 | 0 |  |  |  |  | 100%
10.1 | Set up Elasticsearch and Kibana to index relevant data | Cristian Santaroni & Francesco Fortunato | 2 | 2 | 0 | 5 | 2023-10-23 | 2023-10-28 | 6 | 100%
10.2 | Create dashboards to display user and POI insights | Cristian Santaroni & Francesco Fortunato | 2 | 2 | 0 | 5 | 2023-10-23 | 2023-10-28 | 6 | 100%
11 | Website Aesthetics Enhancement |  | 5 | 5 | 0 |  |  |  |  | 100%
11.1 | Aesthetics Improvement | Cristian Santaroni | 5 | 5 | 0 | 5 | 2023-10-23 | 2023-10-28 | 6 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 150 | 150 | 0 | 25 | 6 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 150 | 144 | 138 | 132 | 126 | 120 | 114 | 108 | 102 | 96 | 90 | 84 | 78 | 72 | 66 | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 6
[10 empty] | ESTIMATE | 150 | 148 | 142 | 138 | 134 | 128 | 123 | 116 | 108 | 100 | 91 | 86 | 80 | 75 | 69 | 61 | 55 | 48 | 42 | 37 | 31 | 25 | 18 | 11 | 5 | 2021
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 2 | 6 | 4 | 4 | 6 | 5 | 7 | 8 | 8 | 9 | 5 | 6 | 5 | 6 | 8 | 6 | 7 | 6 | 5 | 6 | 6 | 7 | 7 | 6 | 5 | 150
[10 empty] | HRS REMAINING | 148 | 142 | 138 | 134 | 128 | 123 | 116 | 108 | 100 | 91 | 86 | 80 | 75 | 69 | 61 | 55 | 48 | 42 | 37 | 31 | 25 | 18 | 11 | 5 | 0 | 1871

## Release Backlog
SCRUM PROJECT MANAGEMENT GANTT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | User Registration and Authentication | User Interface Login | Realizing the html page which is composed by a welcome message with a button that allows to log-in with its own facebook account. | Cristian Santaroni | 2 | Completed |  | Not Started | 1
High | 1 | User Registration and Authentication | Implement user registration with Facebook login | Implement FB authentication flow | Francesco Fortunato | 4 | Completed |  | In Progress | 2
High | 1 | User Registration and Authentication | Develop user authentication system | Implement the flow which recognize if a user after log-in with its facebook account has or not an account in PlaceAdvisor. If the user doesn't have an account, it should be created automatically and saved in the db, otherwise he should be redirected in the home-page | Cristian Santaroni & Francesco Fortunato | 8 | Completed |  | Completed | 4
Middle | 2 | Point of Interest (POI) Information | OpenTrip Map API integration | Using the API the user should be able to check all the places within a ray for a specific city also specifying which type of place he wants to see | Cristian Santaroni | 2 | Completed |  |  | 8
Middle | 2 | Point of Interest (POI) Information | OpenWeatherMap API Integration | The user should be able to check the weather by displaying an icon indicating the various types of weather. This is done by calling the OpenWeatherMap API which return all this information | Cristian Santaroni | 2 | Completed |  |  | 16
Middle | 2 | Point of Interest (POI) Information | HERE API integration | The user should be able to identify the place inside the map, this is done by calling HERE API which marks the point of interest. | Francesco Fortunato | 2 | Completed |  |  | 24
Middle | 2 | Point of Interest (POI) Information | User Interface Research Bar | The user should be able to searche places starting from a city, deciding which is the ray and specifiyng which is the category of the place he is interested. This is done by inserting a search bar for the cities, a drop-down menu for the category of the places and an area in which the user can insert the ray. | Cristian Santaroni | 3 | Completed |  |  | 40
Middle | 2 | Point of Interest (POI) Information | User Interface Details POI | Whenever is possible it is useful to show to the user, all the details of the place, like an historical description if it is an archeological place etc. | Francesco Fortunato | 3 | Completed |  |  | 80
Middle | 2 | User Reviews and Ratings | Develop API endpoints to retrieve reviews and ratings for specific POIs | Develop the endpoint such that given a specific user, it provides all its reviews and rating. | Cristian Santaroni | 3 | Completed
High | 2 | User Reviews and Ratings | Create a database for storing user reviews and ratings | Behind the web application is needed a database wich stores the information about the users , like their name,surname,email and username within all their reviews and feedback that they have made. | Francesco Fortunato | 8 | Completed
High | 2 | User Reviews and Ratings | User Interface for display and submit reviews | Create an html panel, which allow the user to write the reviews about the searched point of interest. This should be done in the same page in which the place searched is shown. | Cristian Santaroni | 1 | Completed
High | 3 | Photo Upload Integration | Integrate Google Photos API | Using the Google API the user should be able to insert an image from its own google photo for each review. This is done adding a button which send the user to the page in which you choose the photos | Cristian Santaroni | 3 | Completed
Middle | 3 | Photo Upload Integration | Implement choosing photo | After clicking the button before, the user should be able to choose the photo. | Cristian Santaroni | 3 | Completed
Middle | 3 | Photo Upload Integration | Implement attaching photo to review | After choosing the photo, it should be added to the review and then published within it. | Francesco Fortunato | 6 | Completed
Middle | 3 | User Profile | Create User Profile Page | The user sould be able to see all his information, this should be done by taking the information from the database e displaying them like a simple page which summarize this information | Cristian Santaroni | 6 | Completed
Middle | 3 | Logout and Delete Account |  | In the same page of the user profile , we will have a simple "delete button" which delete the account from the database, including also its review and feedbacl. Then in the navbar should be implemented another button which allows to do the logout by simply eliminating the cookies of the user. | Cristian Santaroni | 4 | Completed
Middle | 3 | Feedback Service | Create a feedback form for users | The user should be able to write his opinion about the general service offered, sending it to the customer care. This is done by clicking a button "Write a feedback" inside his personal area. | Cristian Santaroni & Francesco Fortunato | 6 | Completed
Middle | 3 | Feedback Service | Develop a backend system for feedback | The backend system is realized in a way such that the user send his feedback and it is saved in a queue. Whenever the service devoted to read the feedback is launched we can see the feedback and set the status of the feedback as "Visualized by the customer Care " in the personal area of the user. | Cristian Santaroni & Francesco Fortunato | 8 | Completed
Middle | 4 | API Documentation | Create and publish API documentation | It is need to provide a graphical interface which show from a graphical point of view the REST inferface | Francesco Fortunato | 8 | Completed
High | 4 | User Registration and Authentication (Pt. 2) | Implement authentication sessions | It should be possible for the user that after a while, he doesn't need to login everytime, but the system should mantain cookies. This one, is used from the system to mantain a session for the user for a certain amount of time. Then is needed another cookie that support the first one, in order to not logout the user, it will refresh the first one when the user is active. | Cristian Santaroni | 2 | Completed
Middle | 4 | User Registration and Authentication (Pt. 2) | Enable HTTPS for secure communication | It is implemented using a certificate, an authentication and more in general using SSH | Cristian Santaroni & Francesco Fortunato | 6 | Completed
Middle | 5 | Customer Care Chat | Implement a real-time chat service | The user and the customer care needs to chat between them. We have to implement a button in the user profile page "chat with customer care". This sends the user to a new page in which you can chat with and type your questions only when the support reply first. Indeed the employee should login through a form and then he will see the list of the user with which to chat | Cristian Santaroni & Francesco Fortunato | 8 | Completed
Middle | 5 | Dashboard with Kibana and Elasticsearch (supported by Logstash) | Set up Elasticsearch and Kibana to index relevant data | To set up Elasticsearch and kibana we need to modify the docker compose meaning that Elasticsearch and Kibana are two containers. To work with Kibana we must have Elasticsearch with all the information that are inside the db and for this reason, the first step is to create indexes using Postman, that are referred to users,reviews and cities. After this we have to send the information from the database to Elasticsearch, this is done using Logstash. We have to configure the .config file which define which is the input (data from the db) and which is the output to send these data ( the corresponding index in ElasticSearch) | Cristian Santaroni & Francesco Fortunato | 2 | Completed
Middle | 5 | Dashboard with Kibana and Elasticsearch(supported by Logstash) | Create dashboards to display user and POI insights | To create the dashboards we have visit the local webpage of kibana and creating a single dashboard with all the charts that we are interested. | Cristian Santaroni & Francesco Fortunato | 2 | Completed
Middle | 6 | Website Aesthetics Enhancement | Improving the style of the webapp | To realize the style of the webpage we use html combined with css, in particular using also bootstrap which can help providing quickly styles to use. | Cristian Santaroni | 5 | Completed

## User Stories
SCRUM PROJECT MANAGEMENT GANTT CHART
USER STORIES
As a | I want to | In order to | ADDED BY | DATED ADDED
New user | register inside the web application using my Facebook account | access the service | Cristian Santaroni & Francesco Fortunato | 2023-09-22
Registered User | be able to log in with my Facebook credentials | save time and avoid creating a new account | Cristian Santaroni & Francesco Fortunato | 2023-09-22
User | search for points of interest in a specific area or city | discover new places to visit | Cristian Santaroni & Francesco Fortunato | 2023-09-24
User | view detailed information about a point of interest, including its address, historical facts, and other relevant details | make informed decisions about visiting it | Cristian Santaroni & Francesco Fortunato | 2023-09-25
User | read reviews and ratings of points of interest from other users | get insights into their experiences | Cristian Santaroni & Francesco Fortunato | 2023-09-25
User | leave my own reviews and ratings for points of interest | share my opinions and help others make informed choices | Cristian Santaroni & Francesco Fortunato | 2023-09-26
User | login with Google and upload and attach photos to points of interest | visually share my experiences with others | Cristian Santaroni & Francesco Fortunato | 2023-09-26
User | access my user profile page | see all my details and view the list of the feedbacks and reviews I have submitted | Cristian Santaroni & Francesco Fortunato | 2023-09-26
Registered user | have the ability to log out of my PlaceAdvisor account and delete my account | ensure the security and privacy of my data and to have control over my account status | Cristian Santaroni & Francesco Fortunato | 2023-09-27
User | provide feedback or suggestions about the app's features and functionality | improve the quality of service | Cristian Santaroni & Francesco Fortunato | 2023-09-28
User | access to analytics and insights about points of interest | gain a better understanding of popular destinations and trends | Cristian Santaroni & Francesco Fortunato | 2023-09-28
Customer Care | log in inside web application | find if there are some users that need help | Cristian Santaroni & Francesco Fortunato | 2023-09-29
User | initiate a real-time chat with support representatives | get assistance with app-related issues | Cristian Santaroni & Francesco Fortunato | 2023-09-29
Customer Care | chat with users of the web application | assist the users and respond to their questions | Cristian Santaroni & Francesco Fortunato | 2023-09-30
User/Developer | access API documentation | understand how to use and to integrate with the PlaceAdvisor API effectively | Cristian Santaroni & Francesco Fortunato | 2023-10-02
user | my authentication session to persist securely | have a seamless experience and not re-login frequently | Cristian Santaroni & Francesco Fortunato | 2023-10-02
security-conscious user | access PlaceAdvisor via a secure HTTPS connection | protect my data and ensure secure communication | Cristian Santaroni & Francesco Fortunato | 2023-10-03
developer | integrate Docker Compose | simplify the deployment and scaling of our application components and ensure consistent development and production environments | Cristian Santaroni & Francesco Fortunato | 2023-10-03
User | a dashboard with Kibana and Elasticsearch for insights into user and POI data | make data-driven decisions and gain valuable insights | Cristian Santaroni & Francesco Fortunato | 2023-10-04
Administrator | a dashboard with Kibana and Elasticsearch for insights into users and POI data | get insights for my website | Cristian Santaroni & Francesco Fortunato | 2023-10-04
User | the pages of the PlaceAdvisor website to have an improved aesthetic design | have a visually pleasing and engaging experience while using the platform | Cristian Santaroni & Francesco Fortunato | 2023-10-05